**Surgical Optimization Workplan**

Chair: Carl Olden, MD

Meeting Dates/Times: First Tuesday 7-8:30AM

Draft Focus Areas

|  |
| --- |
| **Focus Areas** |
| **Preoperative Anemia management**Early identification and diagnosis, targeted treatment (iron, EPA, or transfusions as needed), nutritional optimization, coordination of multidisciplinary care, and monitoring before surgery; population level management of blood products  |
| **Preoperative management of Glycemic Status for people with and without diabetes**: Early screening for glucose dysregulation, nutritional optimization, preoperative glucose monitoring, stress and inflammation management, judicious use of pharmacologic interventions if needed |
| **Payment reform and employer strategies:** value-based models of payment, anemia and glycemic status employer screenings |
| **Multidisciplinary Collaboration/Coordination**Roles of primary care and surgical providers in optimization |

Draft Stakeholder Audiences

* Primary Care
* Surgical Providers (Surgeons/Proceduralists, Anesthesiologists, Internists/Other Post-op Care Providers)
* Hospitals & Surgery Centers
* Health Plans
* Employers

Timeline

|  |  |  |  |
| --- | --- | --- | --- |
| **Month** | **Topics**  | **Milestones** | **Notes** |
| January | ~~Introductions~~ | ~~Finalize Charter~~ | ~~Charter will be approved at January Bree meeting~~ |
| February | Existing Evidence/Guideline ReviewBrainstorm focus areas | Finalize Focus Areas |  |
| March | Finalize focus areas**Objective: Finalize Focus Areas** | Finalize Focus Areas | Chair provides update at Bree meeting |
| April | Evidence Review Focus area 1Objective: Draft guidelines for Focus Area 1 |  |  |
| May | Evidence Review focus area 2 Objective: Draft guidelines for Focus Area 2 |  | Chair provides update at Bree meeting |
| June | Evidence Review focus area 3Objective: Draft guidelines for Focus Area 3 |  |  |
| July  | Evidence Review focus area 4 |  | Chair provides update at Bree meeting |
| August | TBD |  |  |
| September | First Draft Review | Finalize First Draft | First Draft will be approved at September Bree Meeting |
| October | Public Comment Month |  |  |
| November  | Final Draft Review | Finalize Report | Final Draft will be approved at September Bree Meeting |